**POST-2015 FRAMEWORK FOR DISASTER RISK REDUCTION CONSULTATION WORKPLAN IN NIGERIA**

**January – March 2013**

**INTRODUCTION:**

The consultation on the Post-2015 Framework on Disaster Risk Reduction (the successor of the Hyogo Framework for Action) is a broad consultative process to build consensus on the global framework with multi-stakeholders involvement which will be flexible and efficient.

This current process was launched in Geneva in March 2012 by the Special Representative of the UN Secretary-General for Disaster Risk Reduction (SRSG), Margareta Wahlström and his Excellency Yoichi Otabe, the Japanese Ambassador to the International Organizations in Geneva.

The essence of this is to review the performance of the *Hyogo Framework for Action 2005-2015 – Building Resilient Nations and Communities to Disasters* and chart a new and realistic course towards improving on the future performance, defining objectives and priorities of the successor of the Hyogo Framework for Action and ensure reduced vulnerabilities and risks induced by natural hazards and human-made processes.

The post-2015 framework on DRR will to a very great extent create the Road Map towards achieving the sustainable development agenda.

It is also very important to note that, the framework will also show the direction on how the implementation will be decentralised, empower and enhance the participation of the local communities at the grassroots level towards enhancing their resilience.

This broad consultative process is meant to bring in inputs from all stakeholders that have been involved in the process as well as those who have never been involved thereby widening the scope of consultations, discussions and contributions as every sector has a stake in the development and sustainability of the people wellbeing to ensure their resilience.

Nigeria being a major and a very important factor in the global Arena is definitely not going to be set aside in this major global event especially with regard to the enormous disaster risks and high level of vulnerability that still persists within the country.

**Referring to the post-2015 development agenda and to the sustainable development goals, Ms Wahlström said that "ensuring disaster risk reduction considerations are included will be critical to ensuring the overarching goal of resilience is achieved”**

It is therefore, necessary that the consultations around a post-2015 framework on DRR must harness inputs and ideas from all of these stakeholders including national governments, local governments and communities, Parliamentarians, academics and scientists, the private sector, NGOs, international agencies and regional intergovernmental bodies and groups.

**METHODOLOGY:**

The exercise is preceded by a literature review of work done on DRR in Nigeria, followed by multi-stakeholder sessions at national and state levels.

At the national level, sessions would be held with stakeholders, government ministry, department and agencies including Civil Society Organisations, Trade Union/Professional organisations. Each will make presentation on the work they do on DRR in the Federal Capital Territory for National Level.

**STATES VISITS:**

Nigeria is divided into 36 States including a Federal Capital and the whole country is divided into six Geo-Political Zones hence, the reason for the selection of the six states of Rivers, Enugu, Lagos, Benue, Kaduna and Adamawa as a fair representation of the country in view of the socio-cultural sensitivity of the Nigerian Nation in order to enable the various groups which are also diverse in nature have a sense of belonging and involvement in the process.

Similar exercise as at the national level would be replicated at zonal level in each of the selected state to present the zone. This will include paper presentation, discussions, question and answer, experience sharing, exhibition etc.

The sessions at state level will take almost a whole day which will entail travelling to each of the six states which will require travelling, accommodation and possibly some refreshments.

The 3 days assigned to each state includes one day travelling and two days meetings/consultation with the identified groups.

Detailed Work Plan and Guide for Consultations are provided below.

**WORKPLAN**

**POST-2015 FRAMEWORK FOR DISASTER RISK REDUCTION CONSULTATION IN NIGERIA**

**FORA AND LOCATION FOR STAKEHOLDERS CONSULTATION:-**

ECOWAS – ABUJA

NEMA -ABUJA

**SIX (6) ZONAL LOCATIONS**

NORTH-EAST ZONE - BAUCHI STATE

NORTH-WEST ZONE - KADUNA STATE

NORTH-CENTRAL-ZONE - NASARAWA STATE

SOUTH-EAST ZONE - ENUGU STATE

SOUTH- SOUTH - AKWA IBOM STATE

SOUTH-WEST -LAGOS STATE

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **S/NO** | **ACTIVTITY** | **LOCATION** | **IDENTIFIED STAKEHOLDERS** | **PERIOD** | **DURATION** |
|  | Literature Review of DRR activities in Nigeria  | ABUJA |  | Jan 26th - 2nd Feb  | 8days |
|  | Identification, consultation and sensitisation of stakeholders | Abuja and Zonal Level |  Listed below | 1st - 20th February | 20 days  |
|  | Dispatch of notice /invitation for Stakeholders Consultation Forum  | Abuja and Zonal Level | Listed below | 20th -28TH February | 8 days |
|  | Meeting and Consultation Forum with Stakeholders Representatives at National Level  | FEDERAL CAPITAL TERRITORY -ABUJA | National Emergency Management AgencyFederal Ministry of EnvironmentFederal Ministry of Health Federal Ministry of Water ResourcesFederal Ministry of Agriculture Federal Ministry of EducationFederal Ministry of Science and TechnologyFederal Ministry of National PlanningFederal Ministry of FinanceFederal Ministry of Women Affairs and Social Development.Federal Road Safety Corps**National Assembly;**- House Committee on Disaster Management , House Committee on Environment ,Senate Committee on Environment, Senate Committee on Special Duties Federal Ministry of Works, Housing and Urban developmentFederal Capital Development Authority Nigeria Metrological ServiceNigeria Hydrological Service AgencyNigeria MilitaryNigeria Police ForceCivil Society Organisations and networks-4 Nigerian Red Cross SocietyNigeria Security and Civil Defence CorpsECOWASUNICEFUNDPUN-WomenUN-HabitatChristian Association of NigerianJamaatu Nasir IslamNigeria Chamber of CommerceManufacturer Association of Nigeria (MAN)National Insurance Commission National Council of Women SocietyNigeria Institute of Architect Nigeria Society of EngineersNigeria Institute of Town Planner | 19th Feb | One Day |
|
| 3 | NEMA | ABUJA |  | 26TH Feb | One Day |
|  | Meeting and Consultation with ECOWAS |  |  | 28TH Feb | One Day |
| 8. | Identification and consultation with Stakeholders in one State in North-East Geo-Political Zone (Bauchi States)  | BAUCHI | National Emergency Management AgencyFederal Ministry of EnvironmentFederal Ministry of Health Federal Ministry of Water ResourcesFederal Ministry of Agriculture Federal Ministry of EducationFederal Ministry of Science and TechnologyFederal Ministry of National PlanningFederal Ministry of FinanceFederal Ministry of Women Affairs and Social Development.Federal Road Safety Corps**National Assembly;**- House Committee on Disaster Management , House Committee on Environment ,Senate Committee on Environment, Senate Committee on Special Duties Federal Ministry of Works, Housing and Urban developmentFederal Capital Development Authority Nigeria Metrological ServiceNigeria Hydrological Service AgencyThe Nigeria MilitaryNigeria Police ForceCivil Society Organisations and networks-4 Nigerian Red Cross SocietyNigeria Security and Civil Defence CorpsECOWASUNICEFUNDPUN-WomenUN-HabitatChristian Association of NigerianJamaatu Nasir IslamNigeria Chamber of CommerceManufacturer Association of Nigeria (MAN)National Insurance Commission National Council of Women SocietyNigeria Institute of Architect Nigeria Society of EngineersNigeria Institute of Town Planner | 4th-March |  |
|  | Identification and consultation with Stakeholders in one State in North-West Geo-Political Zone -(Kaduna States)  | KADUNA | National Emergency Management AgencyFederal Ministry of EnvironmentFederal Ministry of Health Federal Ministry of Water ResourcesFederal Ministry of Agriculture Federal Ministry of EducationFederal Ministry of Science and TechnologyFederal Ministry of National PlanningFederal Ministry of FinanceFederal Ministry of Women Affairs and Social Development.Federal Road Safety Corps**National Assembly;**- House Committee on Disaster Management , House Committee on Environment ,Senate Committee on Environment, Senate Committee on Special Duties Federal Ministry of Works, Housing and Urban developmentFederal Capital Development Authority Nigeria Metrological ServiceNigeria Hydrological Service AgencyThe Nigerian MilitaryNigeria Police ForceCivil Society Organisations and networks - 4 Nigerian Red Cross SocietyNigeria Security and Civil Defence CorpsECOWASUNICEFUNDPUN-WomenUN-HabitatChristian Association of NigerianJamaatu Nasir IslamNigeria Chamber of CommerceManufacturer Association of Nigeria (MAN)National Insurance Commission National Council of Women SocietyNigeria Institute of Architect Nigeria Society of EngineersNigeria Institute of Town Planner  | 6TH -MARCH | One day |
|  | Identification and consultation with Stakeholders in one State in North Central Geo-Political Zone (Nasarawa States)  |  **NASARAWA** | National Emergency Management AgencyFederal Ministry of EnvironmentFederal Ministry of Health Federal Ministry of Water ResourcesFederal Ministry of Agriculture Federal Ministry of EducationFederal Ministry of Science and TechnologyFederal Ministry of National PlanningFederal Ministry of FinanceFederal Ministry of Women Affairs and Social Development.Federal Road Safety Corps**National Assembly:**- House Committee on Disaster Management , House Committee on Environment ,Senate Committee on Environment, Senate Committee on Special Duties Federal Ministry of Works, Housing and Urban developmentFederal Capital Development Authority Nigeria Metrological ServiceNigeria Hydrological Service AgencyThe Nigerian MilitaryNigeria Police ForceCivil Society Organisations and networks -4 Nigerian Red Cross SocietyNigeria Security and Civil Defence CorpsECOWASUNICEFUNDPUN-WomenUN-HabitatChristian Association of NigerianJamaatu Nasir IslamNigeria Chamber of CommerceManufacturer Association of Nigeria (MAN)National Insurance Commission National Council of Women SocietyNigeria Institute of Architect Nigeria Society of EngineersNigeria Institute of Town Planner  | 11TH -MARCH |  |
|  | Identification and consultation with Stakeholders in one State in South East Geo-Political Zone -(Enugu, States)  | ENUGU | National Emergency Management AgencyFederal Ministry of EnvironmentFederal Ministry of Health Federal Ministry of Water ResourcesFederal Ministry of Agriculture Federal Ministry of EducationFederal Ministry of Science and TechnologyFederal Ministry of National PlanningFederal Ministry of FinanceFederal Ministry of Women Affairs and Social Development.Federal Road Safety Corps**National Assembly;**- House Committee on Disaster Management , House Committee on Environment ,Senate Committee on Environment, Senate Committee on Special Duties Federal Ministry of Works, Housing and Urban developmentFederal Capital Development Authority Nigeria Metrological ServiceNigeria Hydrological Service AgencyThe Nigerian MilitaryNigeria Police ForceCivil Society Organisations and networks - 4 Nigerian Red Cross SocietyNigeria Security and Civil Defence CorpsECOWASUNICEFUNDPUN-WomenUN-HabitatChristian Association of NigerianJamaatu Nasir IslamNigeria Chamber of CommerceManufacturer Association of Nigeria (MAN)National Insurance Commission National Council of Women SocietyNigeria Institute of Architect Nigeria Society of EngineersNigeria Institute of Town Planner  | 15TH MARCH |  |
|  | Identification and consultation with Stakeholders in one State in South –South Geo-Political Zone Akwa Ibom States)  |  **AKWA IBOM** | National Emergency Management AgencyFederal Ministry of EnvironmentFederal Ministry of Health Federal Ministry of Water ResourcesFederal Ministry of Agriculture Federal Ministry of EducationFederal Ministry of Science and TechnologyFederal Ministry of National PlanningFederal Ministry of FinanceFederal Ministry of Women Affairs and Social Development.Federal Road Safety Corps**National Assembly;**- House Committee on Disaster Management , House Committee on Environment ,Senate Committee on Environment, Senate Committee on Special Duties Federal Ministry of Works, Housing and Urban developmentFederal Capital Development Authority Nigeria Metrological ServiceNigeria Hydrological Service AgencyThe Nigeria ArmyMilitaryNigeria Police ForceCivil Society Organisations and networks Nigerian Red Cross SocietyNigeria Security and Civil Defence CorpsECOWASUNICEFUNDPUN-WomenUN-HabitatChristian Association of NigerianJamaatu Nasir IslamNigeria Chamber of CommerceManufacturer Association of Nigeria (MAN)National Insurance Commission National Council of Women SocietyNigeria Institute of Architect Nigeria Society of EngineersNigeria Institute of Town Planner | 18TH MARCH |  |
|  | Identification and consultation with Stakeholders in one State in South-West Geo-Political Zone -(Lagos, States)  | LAGOS | National Emergency Management AgencyFederal Ministry of EnvironmentFederal Ministry of Health Federal Ministry of Water ResourcesFederal Ministry of Agriculture Federal Ministry of EducationFederal Ministry of Science and TechnologyFederal Ministry of National PlanningFederal Ministry of FinanceFederal Ministry of Women Affairs and Social Development.Federal Road Safety Corps**National Assembly;**- House Committee on Disaster Management , House Committee on Environment ,Senate Committee on Environment, Senate Committee on Special Duties Federal Ministry of Works, Housing and Urban developmentFederal Capital Development Authority Nigeria Metrological ServiceNigeria Hydrological Service AgencyThe Nigerian MilitaryNigeria Police ForceCivil Society Organisations and networks - 4 Nigerian Red Cross SocietyNigeria Security and Civil Defence CorpsECOWASUNICEFUNDPUN-WomenUN-HabitatChristian Association of NigerianJamaatu Nasir IslamNigeria Chamber of CommerceManufacturer Association of Nigeria (MAN)National Insurance Commission National Council of Women SocietyNigeria Institute of Architect Nigeria Society of EngineersNigeria Institute of Town Planner  | 20TH MARCH |  |
| 16. | Review and validation of meeting outcomes with NEMA and Stakeholders | ABUJA | STAKEHOLDER REPRESENTATIVES FORUM | 22ND MARCH |  |
| 17. | Documentation and submission of Final Report. | ABUJA |  | 23rd March |  |
|  | Visit of SRSG |  ABUJA | JUNE, 2013 |  |  |

**GUIDE TO THE FACILITATOR OF THE POST-2015 FRAMEWORK ON DRR CONSULTATION**

*Post-2015 DRR framework consultations*

* Conduct multi-stakeholder discussions on post-2015 framework according to the guidance documents provided by ISDR.
* Identify and contact stakeholders in Government, private sector, civil society, gender etc. and undertake individualized contact.
* Organize short meetings in collaboration with NEMA to build common views from interested parties and partners.
* Facilitate discussions on post-2015 DRR framework that embrace current HFA implementation including National platform effectiveness, the main ideas developed to build the new DRR framework and process to conduct further national consultations in an organized manner.
* Liaise and coordinate with ECOWAS, using Nigeria’s experience, during Regional meetings and sharing the acquired experience with the other countries in West Africa.