Proposed Strategy for Building Resilience to Tsunamis

In the Indian Ocean 2006-2008

Background and Context:

Following the devastating tsunami disaster on 26 December 2004, the international community has made concerted efforts to address the humanitarian, recovery and development needs of the countries and population affected. Recognizing the urgency to mobilize efforts and resources towards establishing an early warning system for the Indian Ocean region, the ISDR secretariat, in cooperation with UNESCO’s Intergovernmental Oceanographic Commission (IOC) and other agencies, developed the tsunami early warning initiative “Evaluation and Strengthening of Early Warning Systems in countries affected by the 26 December 2004 Tsunami”. As part of the UN Flash Appeal for tsunami affected countries, the above initiative provided the initial preparatory steps and coordination mechanisms towards the establishment of a comprehensive people-centered early warning system for the Indian Ocean region.

With generous donor contributions and the collective efforts of partners from the UN, regional organizations and research organizations, the project has targeted technical core system implementation, community-level approaches, public awareness, and integrated risk management. During 2005, substantial progress has been made towards the development of capacities to support tsunami early warning system in the Indian Ocean. Key achievements include:

- Establishment of the core technical elements of a regional tsunami early warning system is on track and to be completed by June 2006.

- Coordination of joint efforts of many key organizations in the UN and the region, linking the tsunami warning system to other hazard warning systems and to disaster management institutions.

- Significant progress towards awareness raising and capacity building in advocacy with effective engagement of the media and non-governmental organizations.

- Provision of an example of an integrating vehicle for supporting the implementation of the Hyogo Framework for Action 2005-2015: Building the resilience of nations and communities to disasters.

- Engagement of a wide range of partners and donor contributions, which has brought an added-value to the diversity of activities, and a more coordinated and coherent approach to the problem, thus extending the reach and effectiveness of inputs and resources.

During 2005, several activities were completed and major accomplishments include the development of regional inter-governmental processes to support tsunami early warning system in the Indian Ocean, completion of national needs assessments for sixteen countries in the Indian Ocean region in both Asia and Africa, the development of vulnerability assessment methods in selected communities, the increased coordination and networking among national disaster management offices and their local and regional counterparts, tailored tsunami public awareness and education initiatives, and community-based approaches to preparedness and mitigation.

However, while the Flash Appeal initiative has provided a sound basis for strengthening tsunami early warning systems of countries in the Indian Ocean region, much more work remains to be done to build the long-term sustained national capacities for resilience to tsunamis and to ensure the integration of these systems in development and disaster risk reduction strategies.

A strategy for building resilience:

To develop and sustain a systematic comprehensive people-centered early warning system, long-term strategic planning coupled with financial and human resources allocations will be essential. ISDR secretariat, in its capacity and responsibility to facilitate the implementation of the Hyogo Framework for Action 2005-2015, proposes the attached “Strategy for Building Resilience to Tsunamis in the Indian Ocean for 2006-2008”. The strategy aims to capitalize on achievements of the 2005 activities, including the continued development of collective inter-agency efforts and enhanced linkages and partnerships. It will complement the continuing initiatives by UNESCO-IOC and WMO to strengthen the design and coordination of the core warning system, while shifting the emphasis toward building resilience to tsunamis in the context of other hazards and disaster risk management and reduction.

Guided by the Hyogo Framework for Action 2005-2015, the strategy’s overall goal will be Hyogo’s strategic goal 2, which is the “Development and strengthening of institutions, mechanisms, and capacities to build resilience to hazards”. The strategy – detailed in the attached matrix – will support the implementation of priorities for action identified in the Hyogo Framework for Action, and will develop activities towards the achievement of the following three “Priorities for Action” from Hyogo Framework for Action 2005-2015:

- Identify, assess and monitor disaster risks and enhance early warning;

- Use knowledge, innovation and education to build a culture of safety and resilience at all levels;

- Strengthen disaster preparedness for effective response at all levels.

In addition, the strategy will draw on the conclusions and findings of the sixteen-needs assessment missions carried out in sixteen countries bordering the Indian Ocean rim during 2005. The national assessment missions provided an opportunity to define the components and implementation actions of tsunami early warning and mitigation systems and to identify related capacity building opportunities, and the consolidated report, published in December 2005, provides a summary of the types of guidance documents and capacity building activities that will help to catalyze national actions.

An overall regional summary of findings indicated that:

- Most countries have established or strengthened their disaster management laws, national platforms, and national and local coordination mechanisms but not all have specifically addressed the tsunami coordination aspect.

- All participating countries (except Somalia) receive international tsunami warnings from the Pacific Tsunami Warning Center (PTWC) and the Japan Meteorological Agency (JMA) except Somalia, but few countries operate a national tsunami warning centre or have the capacity to receive or provide real-time seismic or sea level data.

- Few participating countries have developed tsunami emergency and evacuation plans and signage or tested response procedures for tsunamis or earthquakes, but much of the information and data needed to develop these plans, such as post-event surveys, inundation modeling, and tsunami hazard and vulnerability assessment, has yet to be collected.

- Many participating countries have assessed local government capacity for disaster preparedness and emergency response but not community preparedness.

- Community education and outreach programmes are being developed but are largely not in place in most participating countries.

- Most countries have made progress developing policies, assessing technological needs, and establishing coordination mechanisms at a national level for tsunami warning and mitigation. But local planning and preparedness activities are being carried out first in selected target areas, or cities and towns, rather than as comprehensive national programmes.

In that respect, the ISDR proposed “Strategy for Building Resilience to Tsunamis in the Indian Ocean for 2006-2008”, has identified six key areas of intended outcomes that build on the ongoing tsunami early warning initiative as well as addressing the strategic goals of Hyogo Framework for Action, the needs and gaps identified in the national needs-assessment reports, and areas that require further strengthening and enhancement on a long-term basis.

Areas of intended outcomes include:

- Disaster management to support institutional capacity-building in disaster risk reduction and management.

- Public awareness to facilitate the enhancement of public awareness regarding tsunami.

- Education to support the strengthening of the education role in early warning and disaster risk reduction.

- Community-based approaches to support the strengthening of preparedness, mitigation and response capacity of local communities.

- Early warning core system to support the completion of the current core system implementation plans.

- Tsunami risk assessment and mitigation to facilitate the coordination of research development and risk assessment in areas at high risk of future tsunami.

ISDR secretariat will aim to ensure that the strategy is mainstreamed and integrated within the joint work programme of the ISDR system, the activities of the ISDR Africa and Asia outreach offices, and the work plan of the ISDR Platform for the Promotion of Early Warning. ISDR regional offices will play key roles in coordinating project activities and further strengthening networks and collaboration at the regional and national levels. In order to sustain activities and outcomes in the region, special attention will be paid to capacity-building needs of ISDR National Platforms and national disaster management institutions in addition to strengthening the coordination mechanisms across regional, national, and local levels.

Moreover, linkages and synergies will be emphasized to promote a comprehensive and development-oriented approach to disaster mitigation, preparedness and response to ensure that early warning systems development is mainstreamed into national disaster risk reduction and development planning, therefore more sustainable. This requires more engagement and follow-up to the implementation of Hyogo Framework for Action and national planning and development processes, including enhanced coordination with governments, UN country teams, and donors. The strategy provides an opportunity to further strengthen inter-agency, multi-partner, and multi-sectoral collaboration towards the implementation of the Hyogo Framework for Action, and building the resilience of communities and nations to tsunamis in the Indian Ocean.

Proposed Strategy for Building Resilience to Tsunamis in the Indian Ocean 2006-2008

| HYOGO Strategic Goal | Development and strengthening of institutions, mechanism, and capacities to build resilience to hazards |
| --- | --- |
| Relevant HYOGO Priorities for Action | Identify, assess and monitor disaster risks and enhance early warning Use knowledge, innovation and education to build a culture of safety and resilience at all levels Strengthen disaster preparedness for effective response at all levels |
| Targeted Countries | All the Indian Ocean Countries |
| Areas of Intended Outcomes | Intended Outputs | Proposed Partner Agencies | Resources Target |
| 1. Disaster Management | Support institutional capacity-building in disaster management through: Supporting the strengthening of ISDR National Platform including tsunami and other hazards entities. Supporting disaster risk reduction activities through the National Disaster Management Office’s (NDMO) mechanism with partner agencies. Mobilisation of UN volunteers with disaster risk reduction expertise to provide technical assistance where required. Promotion of strong linkage and coordination between the NDMO and local, provincial, disaster management authorities. Facilitating the set-up of regional coordination and information exchange mechanisms. Promotion of the integration of disaster risk reduction in coastal zone management. Provision of guidance on warning dissemination mechanisms, from authorities to people at risk. | UNDP Country Offices and BCPR, ADPC, ADRC, UNEP, UNESCAP, UNESCO-IOC / ITIC, PWRI, UNV, ISDR secretariat | US$ 4,000,000 |
| 2. Public Awareness | Facilitate the enhancement of public awareness regarding tsunami through: Dissemination of best practices and lessons learned from tsunami of 2004. Supporting national and local authorities to carry out targeted awareness-raising campaigns through the media and public events. Supporting the development of public information material tailored to local cultures and languages. Supporting the compilation of all-hazard kit (web-based information materials). | ADRC, ADPC, ABU, UNESCO-IOC/ ITIC, IFRC, WMO, OSE, ActionAid, ISDR secretariat | US$ 1,000,000 |
| 3. Education | Support the strengthening of the education role in early warning through: Promotion and support for the integration of natural hazard component into school curriculum. Engagement of members of the education system in developing tsunami educational materials. Training of trainers programmes for schoolteachers and disaster managers. | UNESCO (Education sector and IOC/ITIC), ADRC, ActionAid, UNV, ISDR secretariat | US$1,000,000 |
| 4. Community-based Approaches | Support the strengthening of local communities’ response capability through: Assessment and improvement of community preparedness measures in coastal zones and building on lessons learned from ongoing pilot activities. Development of community tools and methods for effective disaster risk reduction. Targeted-action at tsunami high risk community areas and develop plans to strengthen their capacity and build their resilience (e.g. Padang, Indonesia) Mobilization of a cadre of local volunteers responsible for training communities in disaster preparedness and establishing an effective chain of communication. | UNDP, UNEP, ADRC, ADPC, IFRC, UNESCO (Education sector and IOC/ITIC), UNV, ISDR secretariat | US$ 2,000,000 |
| 5. Early Warning Core System Implementation | Support the completion of the current core system implementation plans through: Support for national tsunami early warning centers. Support regional coordination and inter-governmental processes led by IOC. Clarification and strengthening of roles among national tsunami warning centers, national meteorological centers and NDMOs. Support for a faster and more dependable international communication between tsunami warning centers. | UNESCO-IOC, WMO, JMA, PTWC, ISDR secretariat | US$ 1,000,000* |
| 6. Tsunami Risk Assessment and Mitigation | Facilitate the coordination of research development and risk assessment to provide: Guidance on the application of tsunami-specific structural measures such as tsunami shelters, sea walls, levees. Analysis and detection of historical tsunami records Knowledge exchange and training on hazard map and its application strategy. Identification of hot spots with higher probability of tsunami risk in the near future. Risk factor analysis on tsunami disaster affected population. | USGS, NIED, UNEP, UNU-IEHS, CRED, UNESCO-IOC/ITIC, ISDR secretariat | US$ 500,000 |
| Overall project coordination among the various partners and donors including the strategic overview, resources mobilization and allocation, monitoring, reporting and evaluation of project activities and results. ISDR will also support regional coordination through the contribution of its regional outreach offices in Africa and Asia. | ISDR secretariat / PPEW | US$ 1,000,000 |
| OVERALL project resources required | US$ 10,500,000 |

* Indicative resources assume that UNESCO-IOC and WMO are supported by additional bilateral funding and projects for core system implementation.

Acronyms:

| ABU ADPC ADRC BCPR CRED UNESCAP IEHS IFRC IOC ISDR ITIC | Asia Pacific Broadcasting Union Asian Disaster Preparedness Center Asian Disaster Reduction Center Bureau for Crisis Prevention and Recovery (of UNDP) Center for Research on the Epidemiology of Disasters (of Belgium) UN Economic and Social Commission for Asia and the Pacific Institute for Environment and Human Security (of UNU) International Federation of Red Cross and Red Crescent Societies Intergovernmental Oceanographic Commission (of UNESCO) International Strategy for Disaster Reduction International Tsunami Information Center (of UNESCO) |
| --- | --- |
| JMA NIED OSE PPEW PTWC PWRI UNDP UNEP UNESCO UNU UNV USGS WMO | Japan Meteorological Agency National Research Institute for Earth Science and Disaster Prevention (of Japan) UN Office of the Special Envoy for Tsunami Recovery Platform for the Promotion of Early warning Pacific Tsunami Warning Center (of the United States) Public Works Research Institute (of Japan) United Nations Development Programme United Nations Environment Programme UN Educational, Scientific and Cultural Organization United Nations University United Nations Volunteers Programme United States Geological Survey World Meteorological Organization |